## Stakeholder Analysis
ID | Name | Description | Benefit (Significance) | Harm | Power | Interest | Strategy | Metric
SH001 | Researchers/Developers |  |  |  | High | High | Manage Closely | High
SH002 | Quantum Computing Community |  |  |  | High | Low | Keep Satisfied | Low
SH003 | IBM (and other quantum hardware providers) |  |  |  | Low | High | Keep Informed
SH004 | Academic Institutions |  |  |  | Low | Low | Monitor
SH005 | Industry Partners
SH006 | Funding Bodies

## Communication Matrix
ID | Sender | Receiver | Information | Medium | Frequency
CM001 | Researchers/Developers | Quantum Computing Community | Updates on algorithm advancements and findings | Webinars | Quarterly
CM002 | Researchers/Developers | IBM (and other quantum hardware providers) | Feedback on algorithm performance on devices. | Email | Monthly
CM003 | Funding Bodies | Researchers/Developers | Progress reports and financial accountabilities. | Formal Report | Biannually
CM004 | Academic Institutions | Quantum Computing Community | Sharing theoretical research and explorations. | Research Papers | Annually
CM005 | IBM (and other quantum hardware providers) | Researchers/Developers | Requirements and feedback on algorithm optimization | Meetings | Monthly
CM006 | Industry Partners | Researchers/Developers | Updates on practical applications of the algorithm | Conferences | Annually

## Risk Register
Risk ID | Name | Impact | Probability | Priority | Index | Response | Strategy | Owner | Feasible | Testable | Incomplete | Ambiguous | Inconsistent | Impact
R001 | Identified errors during optimisation algorithm development due to software security vulnerabilities | 2 - High | 3 - Likely | 1 - Urgent | 6 | Patch software and conduct security audit | Mitigate | Me | Y | Y | N | N | N | 1 - Critical
R002 | Encountered unexpected supply chain disruptions (Quantum computer disruptions) | 1 - Critical | 5 - Potentially Never | 1 - Urgent | 5 | Develop alternative virtual Quantum computer contacts | Avoid | Supplier | Y | Y | Y | N | N | 2 - High
R003 | Unavailability of key personnel due to illness | 3 - Medium | 3 - Likely | 2 - Essential | 18 | Establish backup personnel for key roles | Mitigate | Supervisor | Y | N | N | Y | N | 3 - Medium
R004 | Delays in project milestones due to unforeseen regulatory changes | 2 - High | 3 - Likely | 3 - Valuable | 18 | Engage with legal team for compliance checks | Transfer | Supervisor | N | N | Y | N | Y | 4 - Low
R005 | Failure of cloud infrastructure leading to data loss | 1 - Critical | 4 - Unlikely | 1 - Urgent | 4 | Implement regular backups and disaster recovery plans | Mitigate | Supplier | Y | Y | Y | N | Y | 5 - Superficial
R006 | Communication breakdown within teams leading to inefficiencies | 2 - High | 2 - Very Likely | 3 - Valuable | 12 | Improve communication channels & conduct team trainings | Mitigate | Supervisor and me | Y | N | Y | Y | Y
Probability
1 - Certain
2 - Very Likely
3 - Likely
4 - Unlikely
5 - Potentially Never
Priority
1 - Urgent
2 - Essential
3 - Valuable
4 - Desirable
5 - Discretionary
Strategy
Avoid
Mitigate
Transfer
Ignore

## Work Breakdown Structure
Index | Research Activities | Dependencies (Required research activities) | Inputs | Outputs (Deliverables) | Labour | Equipment | Other | Sum | Optimitic Time | Real Time | Pessimistic Time | Estimated Time | Estimated Time + 20% rounded up | Estimated time + Weekends | Semester 1 | Semester 2 | ... | Semester x
1 | literature review
[5 empty] | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 | 0
Total |  |  |  |  | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 | 0

## Scope
Research Topics/Ideas | Lens | Main Concepts/Keywords | Definition | Industry Sector | Research Domain